AI-Powered PDLC Transformation GTM Pack — Set 1: CXO GTM Pack Document 09 of 10

Engagement Model Overview

Three-Phase Delivery: Diagnose, Design, Deliver

DIAGNOSE · DESIGN · DELIVER · Accelerated by AI

Overview: The Three-Phase Engagement Architecture

The AI-Powered PDLC Transformation engagement is structured in three phases that flow in sequence but overlap at their boundaries. Each phase has a defined scope, deliverable set, and success gate before the next phase begins. The design ensures that every programme starts with evidence, every design is grounded in data, and every delivery is measured against a defined baseline.

Phase 1 → Phase 2 → Phase 3 is not a waterfall. Phase 2 Design begins in the final 2 weeks of Phase 1 Diagnose, and Phase 3 quick wins begin in the first month of Phase 3 — before the full programme is deployed. The model is designed for momentum, not sequential gating.

Phase 1: DIAGNOSE — 8 Weeks

What Happens

| Week | Activity | Platform Role | Client Requirement |
| --- | --- | --- | --- |
| 1 | ALM data connection; historical data extraction; team onboarding | Automated API integration with Jira / ADO / Rally | Provide ALM admin credentials; 2-hour onboarding session |
| 2 | Current state VSM generation; preliminary bottleneck identification | AI agents generate VSM from ticket telemetry | Engineering lead review of VSM draft (2 hours) |
| 3–4 | Bottleneck deep-dive; speed/productivity/quality quantification; benchmark overlay | AI analysis; benchmark comparison against 500+ FS peers | 2 x 90-min workshops with engineering and product leads |
| 5–6 | Three-option business case development; ROI modelling; payback and NPV calculation | Financial model generation; scenario analysis | Finance business partner input (4 hours) |
| 7 | Executive presentation preparation; board narrative development | Slide generation support; data visualisation | CTO/CFO review of draft presentation (2 hours) |
| 8 | Executive presentation and decision session; option selection gate | Live dashboard demonstration | Full leadership team (CTO, CFO, CRO minimum) |

Phase 1 Deliverables

Current State VSM (visual + data export) — the single source of truth for the transformation

Bottleneck Register — prioritised list with cost impact per bottleneck

Speed / Productivity / Quality Dashboard — benchmarked against sector peers

Three-Option Business Case — investment, benefit, ROI, payback, NPV for each option

Executive Presentation — board-ready summary with recommendation

Phase 1 Sign-Off Gate — leadership team agreement on which option to proceed with

What 'Success' Looks Like at the Phase 1 Gate

Success at Phase 1: Leadership team has seen the data, understands the bottleneck cost, has reviewed three credible options with business cases, and has selected an option to proceed with. The CFO has signed off on the investment. The CTO has named a programme owner.

Phase 2: DESIGN — Concurrent With Phase 1 Close

What Happens

Phase 2 Design begins in Week 6 of Phase 1, running concurrently with business case finalisation. This overlap ensures that when the executive presentation occurs in Week 8, the selected option already has a high-level design in progress — enabling Phase 3 to begin immediately after approval.

| Design Track | Activity | Timing | Owner |
| --- | --- | --- | --- |
| Option Architecture | Design the technical architecture for the selected option; identify AI agents/tools required | Weeks 6–10 | Lead architect + CTO |
| Governance Design | Define gate structure (Option B); autonomy boundaries; audit requirements (Option C) | Weeks 7–10 | Risk lead + CRO |
| Transformation Playbook | Detailed implementation plan: sequence, milestones, team responsibilities, dependencies | Weeks 8–12 | Programme lead + Engineering |
| Change Management Plan | Stakeholder map; change narrative; adoption strategy; training plan | Weeks 8–12 | Change lead + HR |
| Benefits Tracking Framework | Define KPIs; measurement cadence; reporting format; board reporting template | Weeks 9–12 | Analytics lead + Finance |

Phase 2 Deliverables

Option Design Document — detailed architecture, agent configuration, integration design

Governance Framework — gate definitions, approval workflows, audit trail specification

Implementation Playbook — phased plan with milestones, owners, and dependencies

Change Management Plan — adoption strategy, stakeholder engagement, training schedule

Benefits Tracking Framework — KPIs, measurement cadence, board reporting template

Phase 2 Sign-Off Gate — leadership team review and approval of playbook before Phase 3 kickoff

What 'Success' Looks Like at the Phase 2 Gate

Success at Phase 2: The organisation has a clear, detailed plan for Phase 3. Every stakeholder knows their role. The governance model is agreed. The first 90-day quick wins are identified and resourced. The measurement framework is live. Phase 3 can begin immediately.

Phase 3: DELIVER — Option-Specific Timeline

The Three Delivery Horizons

| Horizon | Timeline | Option A | Option B | Option C |
| --- | --- | --- | --- | --- |
| H1: Quick Wins | Months 1–3 | AI tools at 2 top bottlenecks; 15% LT reduction | AI agents at top 2 steps; gates configured; 20% LT reduction | Autonomous pipeline for 1 product team; 25% LT reduction |
| H2: Core | Months 4–12 | AI tools across all steps; coaching programme | AI agents across 5 steps; all gates live; measurement running | Full autonomous pipeline; human-above governance deployed |
| H3: Scale & Optimise | Months 13–24+ | Extend to 2–3 additional teams; measure + tune | Scale to additional teams; optimise agent performance | Scale to org-wide; prepare Option C extension path |

Platform Role in Each Phase

| Phase | Platform Function | Value Delivered |
| --- | --- | --- |
| Phase 1 Diagnose | ALM data extraction; AI-generated VSM; bottleneck analysis; benchmark overlay; business case generation | 3-month process in 2 weeks; evidence-based baseline; CFO-ready business case |
| Phase 2 Design | Design validation; architecture review; benefits model update; governance gate configuration | Design validated against real data; gates configured before deployment |
| Phase 3 Deliver | Continuous measurement; benefits tracking; agent performance monitoring; board reporting dashboard | Real-time evidence of benefit realisation; early warning on slippage; board confidence |

Client Responsibilities Per Phase

| Phase | Client Must Provide | Estimated Effort |
| --- | --- | --- |
| Phase 1 Diagnose | ALM admin access; 2–4 senior engineering stakeholders; finance business partner (4 hrs); executive team for Week 8 presentation | ~20 hours total client time |
| Phase 2 Design | CTO/CRO engagement on governance design; programme owner nominated; change management resource allocated | ~40 hours total client time |
| Phase 3 Deliver | Programme owner (0.5 FTE); engineering team engagement for each deployment; executive sponsor for quarterly reviews; finance for benefits sign-off | ~0.5–1.0 FTE ongoing |

How the Platform Makes Each Phase Faster and Evidence-Based

The 5× Acceleration Principle

Every phase of the engagement is accelerated by the STUMP. The platform is not a software product being licensed — it is an operational capability that is deployed in service of the consulting programme. Clients do not need to buy, implement, or maintain the platform: it runs as part of the engagement.

Phase 1: Phase 1 is 5× faster because VSM generation is automated from ALM data. No manual data wrangling. No workshop transcription. No consultant estimates.

Phase 2: Phase 2 is more accurate because design decisions are validated against the measured baseline. The design is anchored to real data, not assumptions.

Phase 3: Phase 3 benefits are visible in real time. The platform's measurement dashboard gives the executive team live visibility of benefit realisation — no waiting for quarterly reviews to know if the programme is working.

The platform is the accelerator. The consulting team is the strategy, the change, and the accountability. Together, they deliver transformation outcomes that neither could achieve independently.