PDLC VSM Platform

GTM Pack — Set 2: Pilot Engagement Pack

Pilot Proposal Template

AI-Powered PDLC Value Stream Analysis — Paid Pilot

| Document | Version | Date | Classification |
| --- | --- | --- | --- |
| DOC-SET2-11 | v1.0 | March 2026 | Commercial Confidential |

Executive Summary

This proposal outlines a structured 8-week paid pilot engagement to quantify your software delivery lead time, identify the top 3–5 value stream bottlenecks, and produce a board-ready business case for AI-assisted flow improvement. The pilot is designed to be low-risk, high-speed, and independently verifiable.

Investment: $150,000 fixed fee  |  Duration: 8 weeks  |  Risk: Full-refund guarantee if savings < $500K/year identified

Business Context

The Problem We Are Solving

Average financial services delivery lead time: 34–47 days per feature

Flow efficiency (actual work vs. queue time) averages 17.8% in your sector — 82% of time is waste

Manual bottleneck identification takes 3–6 months of consultant time

Business cases for DevOps investment lack quantified ROI — causing approval delays

DORA benchmark gap analysis requires specialist expertise and months of data collection

What Changes After the Pilot

Real-time VSM dashboard from your existing Jira / Azure DevOps data — no new tooling required

Top 5 bottlenecks identified with hours of waste per quarter, root cause, and industry benchmark comparison

AI-generated improvement roadmap: 12 Quick Wins (90-day), 8 Medium-term (6-month), 5 Strategic (12-month)

Board-ready business case: ROI, payback period, NPV, and scenario modelling

DORA maturity assessment: current band, target band, and a 73-question gap analysis

Scope of Work

Phase 1: Data Onboarding (Weeks 1–2)

| Activity | Owner | Output | Effort |
| --- | --- | --- | --- |
| Jira / ADO export configuration | Client IT + Pilot Lead | CSV data file (25+ fields) | 2 hours client |
| Platform deployment (cloud or on-prem) | Pilot Lead | Running instance on client infra | 1 day |
| ALM connector configuration | Pilot Lead | Phase mapping validated | 4 hours |
| Data quality review | Pilot Lead + Client | Data quality scorecard | 2 hours client |
| DORA source configuration | Client Team Lead | 4 data sources configured | 3 hours client |

Phase 2: AI Analysis (Weeks 3–4)

| Agent | Input | Output | Duration |
| --- | --- | --- | --- |
| VSM Analyzer | ALM export (2,847+ tickets) | Current state VSM: LT, FE, WT by phase | Automated |
| DORA Assessment Agent | 4 configured sources | 73-question gap score, band assignment | Automated |
| Benchmark Agent | VSM + DORA scores | Peer comparison across 12 competitors | Automated |
| Bottleneck Analyzer | VSM + DORA + benchmarks | Top 5 bottlenecks with severity scores | Automated |
| Improvement Generator | All above | 25–35 ranked AI improvement initiatives | Automated |
| Future State Designer | All above | 3 future-state scenarios (Option A/B/C) | Automated |
| Business Case Builder | Future state scenarios | 3 scenarios × ROI / payback / NPV | Automated |

Phase 3: Validation & Calibration (Weeks 5–6)

Stakeholder review session: Pilot Lead presents AI findings to client team lead and 2 engineers

Manual override capability: client team adjusts any AI score via the platform UI

Benchmark calibration: DORA weights adjusted based on team's self-assessment

Business case scenario selection: client selects preferred investment option for CFO presentation

Phase 4: Delivery & Readout (Weeks 7–8)

Executive readout deck (PPT): 15 slides, board-ready, with your organisation's branding guidelines applied

Action plan in the platform: 25+ items with owner, target date, effort estimate, and status tracking

Playbook contextualisation: 3 AI-tailored implementation playbooks (one per scenario)

Platform handover: client team trained, login credentials set up, 30-day post-pilot support included

Deliverables Summary

| # | Deliverable | Format | Audience | Date |
| --- | --- | --- | --- | --- |
| D1 | Current State VSM Dashboard | Platform (live) | Engineering team | Week 3 |
| D2 | DORA Assessment Report | Platform + PDF export | Engineering + CTO | Week 4 |
| D3 | Top 5 Bottleneck Analysis | Platform + slide deck | CTO + VP Eng | Week 4 |
| D4 | AI Improvement Roadmap | Platform + PDF export | CTO + VP Eng | Week 5 |
| D5 | Business Case (3 scenarios) | Platform + slide deck | CFO + CEO | Week 6 |
| D6 | Executive Readout Deck | PowerPoint (15 slides) | Board / ELT | Week 8 |
| D7 | Action Plan (25+ items) | Platform (live) | Team Lead | Week 7 |
| D8 | Implementation Playbooks (×3) | Platform + PDF export | Programme team | Week 8 |
| D9 | Knowledge transfer session | 60-min live session | Platform Admin | Week 8 |

Commercial Terms

Pricing

| Item | Description | Price |
| --- | --- | --- |
| Pilot Fixed Fee | Full 8-week engagement as scoped above | $150,000 |
| Success Guarantee | Full refund if < $500K annual savings identified | Included |
| Post-Pilot Support | 30-day named support contact | Included |
| Scale Licence (optional) | Full platform licence post-pilot | POA |

Risk Mitigation

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| ALM data quality issues | Medium | Data quality scorecard in Week 1; 2-week remediation window |
| Stakeholder availability | Low | Asynchronous review via platform; 1h max per week for client team |
| Data privacy concerns | Low | On-prem deployment option; anonymisation scripts provided |
| Platform performance | Low | Handles 100K+ tickets; horizontal scaling available |
| Findings inconclusive | Very Low | Guaranteed: ≥3 bottlenecks or full refund |

Success Condition: We guarantee identification of ≥3 material bottlenecks and a minimum $500,000 annual savings opportunity. If not achieved, 100% fee refund — no questions asked.

Authorised by: ___________________________   Date: _______________

Client: ___________________________   Title: _______________