PDLC VSM Platform

GTM Pack — Set 2: Pilot Engagement Pack

Risk Register

Pilot Engagement Risk Identification and Mitigation Plan

| Document | Version | Date | Classification |
| --- | --- | --- | --- |
| DOC-SET2-19 | v1.0 | March 2026 | Commercial Confidential |

Risk Rating Scale

| Rating | Likelihood | Impact | Response Required |
| --- | --- | --- | --- |
| Critical (16–25) | Very Likely (5) × Major Impact (4–5) | 5 = >$1M impact or engagement failure | Immediate escalation + contingency plan |
| High (9–15) | Likely (4) × Significant (3–4) | 4 = Significant delay or scope reduction | Weekly monitoring + mitigation action |
| Medium (5–8) | Possible (3) × Moderate (2–3) | 3 = Minor delay, manageable | Fortnightly review |
| Low (1–4) | Unlikely (1–2) × Minor (1–2) | 1–2 = Negligible impact | Monitor only |

Risk Register

| ID | Risk Description | Category | L | I | Rating | Mitigation | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R01 | ALM data export blocked by IT security policy or data governance | Data | 3 | 5 | High | Pre-engage IT lead; offer on-prem option; data NDA | Client PM | Open |
| R02 | Data quality too poor for meaningful VSM (>40% missing resolved dates) | Data | 3 | 4 | High | Data quality scorecard Week 1; heuristic LT for sparse data | Pilot Lead | Open |
| R03 | Key client stakeholder unavailable during critical phases | Resource | 3 | 3 | Medium | Async review via platform; recorded demo as fallback | Client PM | Open |
| R04 | Platform performance degrades with large ticket volumes (>50K) | Technical | 2 | 4 | Medium | Load test before engagement; horizontal scaling available | Pilot Lead | Open |
| R05 | AI agent produces inaccurate bottleneck scores (false negatives) | AI | 2 | 3 | Medium | Manual override in Week 5-6; client SME validation step | Pilot Lead | Open |
| R06 | Executive readout postponed or cancelled | Commercial | 2 | 4 | Medium | 30-day post-pilot support covers rescheduling; async deck delivery | Client PM | Open |
| R07 | Competitor platform already in use; findings challenged | Commercial | 2 | 3 | Medium | Evidence protocol citations; offer parallel run comparison | Pilot Lead | Open |
| R08 | OpenAI/Claude API outage during agent execution | Technical | 1 | 3 | Low | Retry logic built into agents; 48h window for re-run | Pilot Lead | Open |
| R09 | Scope creep: client requests additional teams / data sources | Scope | 4 | 2 | Medium | RACI + change control process; park additional scope for Scale Pack | Pilot Lead | Open |
| R10 | Business case rejected by CFO — ROI not credible | Commercial | 2 | 5 | High | Evidence protocol citations; show conservative scenario; offer reference call | Sponsor | Open |
| R11 | Data privacy or GDPR concern raised mid-engagement | Legal | 2 | 4 | Medium | Anonymisation scripts; on-prem option; DPA in contract | Client PM | Open |
| R12 | Savings guarantee triggered — refund required | Commercial | 1 | 5 | Medium | Pre-qualification in discovery; requires >3 critical bottlenecks to proceed | Pilot Lead | Open |

Risk Review Schedule

| Week | Activity | Owner |
| --- | --- | --- |
| Week 1 | Initial risk register review with Client PM at kick-off | Pilot Lead |
| Weekly | Risk status update in weekly status call | Pilot Lead |
| Week 4 | Mid-point risk review — update ratings after AI run | Pilot Lead + Client PM |
| Week 7 | Pre-readout risk review — flag any unresolved risks | Pilot Lead + Sponsor |
| Week 8 | Closeout risk review — confirm all risks closed or handed over | Pilot Lead |