## Slide 1
AI-POWERED PDLC TRANSFORMATION
ELT Executive Dashboard Briefing
Transformation Status | Benefits Realisation | Strategic Decisions
MONTHLY EXECUTIVE BRIEFING | March 2026

## Slide 2
Transformation Scorecard
Overall programme status at a glance
CURRENT OPTION SELECTED:
Option B — AI Agents + Human Gates ★
−34%
Lead Time vs Baseline
+41%
Flow Efficiency
+38%
Team Productivity
3.1×
ROI vs Plan (4–6× target)
TRANSFORMATION PHASE STATUS
Phase 1 — DIAGNOSE
COMPLETE ✓
VSM mapped, bottlenecks agreed, findings accepted
Phase 2 — DESIGN
COMPLETE ✓
Option B selected, business case approved by CFO
Phase 3 — DELIVER
IN PROGRESS →
Week 8 of 16 — platform live, adoption at 62%

## Slide 3
Benefits Dashboard
Speed, Productivity & Quality ROI — Month 8
SPEED BENEFITS
PRODUCTIVITY BENEFITS
QUALITY BENEFITS
28d → 18d
Lead Time
21%
Flow Eff. Gain
+2.1×
Deploy Freq.
+31%
Productivity
+28%
Story Throughput
62%
Active Users
−22%
Defect Escape
+18%
Test Coverage
−$1.4M
Defect Cost YTD
FINANCIAL SUMMARY
• Investment to date: $1.1M of $1.6M total
• Benefits realised YTD: $2.3M (139% of plan)
• Annualised ROI run-rate: 4.8× (plan: 4–6×)
• Forecast 5-year NPV: $28.4M (plan: $25–35M)

## Slide 4
Gate Governance Status
AI agent gate performance — Option B programme
GATE PERFORMANCE (LAST 30 DAYS)
G1 — VSM Complete
12 of 12
0
100% within 24h
Green
G2 — Options Ready
4 of 4
1
75% within 48h
Amber
G3 — Config Complete
3 of 3
0
100% within 24h
Green
G4 — Go Live
1 of 1
0
100% within 24h
Green
Gate G2 override: CFO requested revised sensitivity analysis before approving Option B business case. Completed within 48h. No impact to programme timeline.

## Slide 5
Decisions Required
Items requiring Executive Steering Committee action
DECISION 1: Option Upgrade Assessment
Review readiness to move from Option B to Option C for the Digital Lending product group
Owner: CFO + CTO
By: 30 April 2026
DECISION 2: Wave 2 Scale Approval
Approve division-wide rollout to Commercial Banking (5 additional teams)
Owner: Executive Sponsor
By: 15 April 2026
DECISION 3: Champions Programme Budget
Approve $180K annual budget for ongoing champions programme
Owner: CFO
By: 15 April 2026

## Slide 6
Outcome Dashboard — Executive View
Three monitoring perspectives, always-on
AI Adoption
How deeply agents/tools are adopted across the PDLC.
• Agent Utilisation Rate
• AI Acceptance Rate
• Human Override Rate
• Time Saved / Agent / Sprint
• Agent ROI Multiple
PDLC Performance (Outcomes)
Delivery outcomes — flow, speed, stability & productivity.
• Lead Time
• Cycle Time
• Flow Efficiency
• Deployment Frequency
• Change Failure Rate
• MTTR
• Cost per Story Point
• Productivity (SP/person-day)
AI Ops & Assurance
Token economics, agent quality, bias, explainability & governance.
• Token Usage & Cost / Sprint
• AI Cost / Story Point
• Agent Success Rate
• Hallucination Rate
• RAG Groundedness
• Bias / Fairness
• Explainability
• Guardrail Compliance
ROI is read on the J-Curve (cost-only): investment → tuition-cost dip → breakeven → compounding savings. Business growth from new features is intentionally excluded — value is engineering cost-efficiency and capacity reinvestment only.